## Sheet1
Beginning of Semester
| Have semester programming planned | You should already know what events you will be hosting this semester and the general timeline and needs of each event. This includes dates, times, A/V, and refreshments.
| Begin reserving space | Begin looking at spaces that can be reserved for your event. Some spaces are not available for reservation until after the semester starts, but knowing this in advance and creating a reservation once the space is available can ensure that you have the ideal space needed for your event.
| Consider contingencies | If your event is outdoors or is reliant on factors outside of your control, you should begin thinking of contingencies and ways you can ensure your event is successful.
| Add events to calendar | Once space is reserved and dates and times are confirmed, be sure to add your event to internal organizational calendars, the GCoE TeamUp Calendar, and your Engage calendar. This will allow you to better communicate your programming to your current and future members.
| Review University Policies | All organizations should review and be familiar with University guidelines and policies that may affect your event.
2-3 Months Before Event
Finalize an event budget
Reserve a space for the event
| Finalize a date and time for event | If you haven't already, you should update your calendars with all details once finalized.
| Identify gifts or item needs | If you are planning to sell something or give a gift to a speaker or presenter, you will need to meet with your financial associate to see if your plan is possible under University guidelines and what the best way to achieve it is.
| Identify potential vendors | Your financial associate will have a list of approved vendors for food, drink, supplies, and more.
| Obtain quotes for services and goods from vendors | Unapproved vendors will require extra time to setup as OU Purchasing will need to approve them. Please work with your financial associate as needed.
| Finalize Minors on Campus Requirements | If you are doing K-12 Outreach, you will need to make sure you are compliant with all Minors on Campus policies*. This includes completing all necessary background checks, trainings, and forms.
*Minors on Campus policies can be found at: https://www.ou.edu/web/landing/policy
5-6 Weeks Before Event
| Select preferred vendor | Work with your financial associate on completing all forms and making sure payment is authorized.
| Finalize space reservation | If you have not already, you should finalize your space reservation for your event. If your event is outdoors, you should also consider reserving an indoor space as backup in case of inclement weather. Remember, your reservation should include setup and clean up time.
| Submit any required approval forms | Your event may require specific forms or permissions depending on what is being done. You will need to work with your advisor on making sure that you complete any requirements imposed by Campus Scheduling or Risk Management.
| Reserve A/V equipment | You should begin reserving or purchasing any additional A/V equipment needed.
| Finalize Promotional/Marketing at Event | You will need to consider if you will need a photographer or camera to take pictures or video of the event. You should also decide if it will be shared on social media and if it will require participants to sign a Talent Release.
| Distribute Talent Releases (if needed) | If your event will be recorded or shared, you will need participants to sign talent releases. These will need to be collected and maintained by your organization. A blank talent release form can be found on the GCoE website or the provided link*.
| Setup registration system (if needed) | If you are doing a RSVP or using volunteers, you will need to create a respective registration form either through Qualtrics or Engage. Submissions should be accessible to all members that are overseeing the event.
*Blank OU Talent Release Form: https://www.ou.edu/content/dam/branding/resources/Talent%20Release%2011_19.pdf
3-4 Weeks Before Event
| Finalize reservations and logistics | You should finalize all logistics and reservations. Make sure that your plan is clear, concise, and communicated to your members, vendors, and advisor.
| Advertise on Social Media | Begin advertising your event on social media so that people interested in attending can plan to be there. If RSVP is needed, make sure that registration links are included.
| Submit event notice to GCoE and MCEE newsletter | You should share your event information in both the GCoE weekly newsletter and the MCEE weekly newsletter. Please note that you can instruct them to be run in the weeks leading up to your event. If RSVP is needed, make sure that registration links are included. All notices must be submitted by Friday at noon to be entered into next week's newsletter.*
| Complete Special Event Form (if needed) | If your event significantly alters a University space or involves the use of tents, structures, platforms, inflatables, fixed equipment, automotive vehicles, aircraft, or other mobile craft in an effort to assemble persons for the purposes of live entertainment/performances, celebrations, attractions, participation, races, walks, runs, parades, fairs, festivals, rides, competitions, sponsored outdoor catered events, and similar occasions, you will need to get approval from the University by completing the Special Events Request Form**.
*GCoE Newsletter: coe_newsletter@ou.edu / MCEE Newsletter: Earth.Links@ou.edu
**Special Events Request Form: https://ou.campuslabs.com/engage/organization/ou-special-events-committee
2-3 Weeks Before
| Post flyers | If you are advertising your event with flyers, you will need to post them at the approved flyer locations throughout the engineering quad. If advertising outside of the engineering quad, you will need to get approval from SGA by completing their RSO Publicity Request Form*.
| Create evaluation plan | Evaluating the success of an event is important for reviewing and improving upon an organization's program. You should consider how to best evaluate your event and create any forms or surveys needed.
| Distribute volunteer registration (if needed) | If volunteers are needed for your event, you will need to open and advertise for volunteer registration. This can be done internally or externally depending on your needs.
* RSO Publicty Request Form: https://ou.campuslabs.com/engage/submitter/form/start/425003
Week of Event
| Setup chalking advertisements | If you are advertising your event with chalking, a week out is generally when you want to do so. Be wary of weather when doing this.
| Confirm facilities and equipment work | Check all A/V equipment to make sure it is functional for your event.
| Confirm food/drink logistics and amounts (if needed) | If your event includes food and drinks, you will need to finalize the amount that is being delivered with the vendor as well as the delivery time and location. Please be sure to have the food delivered a little early in case the vendor is running late.
| Send event reminders | Remind people that you are doing your event through social media channels and send a reminder email to anyone that has registered for your event.
| Prepare materials | Your event may require pens, name tags, attendance sheets, and more. Make sure these materials and papers are created, available, and ready for your event.
| Check weather (if needed) | If your event is outdoors, check the weather and see if you will be able to do your event outdoors or if you will need to relocate or reschedule.
| Obtain access to event venue (if needed) | If your event is after hours or in a locked space, make sure you have access to the space either through card swipe or a key.
Day of Event
Setup room for your event needs
Setup A/V equipment for your event needs
Place attendee list at entrance and have someone there to ensure it is being completed
Be available to receive food and guests
Run the event
| Give away remaining food | If you have leftovers, distribute food to participants, volunteers, or people nearby. Only throw away food if no one will take or eat it.
Collect attendee list
Reset room furniture and collect equipment if it needs to be returned
Collect leftover materials and store for future use and events
cleanup the room
After Event
| Return borrowed keys (if needed) | This must be done on the next business day.
| Take down signs, posters, flyers, and other event advertisements | This must be done in a timely manner.
| Submit your attendance sheet, receipts, and event information to a financial associate | This is necessary if you had any expenses or purchases during your event.
| Send thanks | Be sure to thank all volunteers, external facilitators, and attendees for participating in your event. This should be done the day after your event.
| Debrief your event | Discuss with attendees, volunteers, advisor, and organizational leadership about the event and explore ways to improve the event for future years.